## Sheet1
Day | Tentative Dates | Particulars | Student’s role | Our role
Day 0 - 7 | 25th Dec - 31st Dec,2015 | Researching and Shortlisting colleges and sponsors | NA
Day 8 -13 | 1st Jan - 6th Jan,2016 | Confirmation from sponsors | NA
Day 14 - 21 | 7th Jan - 14th Jan,2016 | Getting confirmation for live project | NA | Telephonic introduction and emailing details of LEAP programme along with the case study of Campus Buddies
Follow-ups with colleges for gettting confirmation
Day 22 - 26 | 14th Jan - 18th Jan,2016 | Receiving resumes and finalizing Campus Buddies Champs | Submitting resumes | Collect resumes
Shortlist candidates
|  |  | Giving interviews | Conduct interviews
Finalize Campus Buddies Champs
Day 27 | 19th Jan, 2016 | Finalise candidates
Day 28 | 20th Jan, 2016 | Induction - LEAP starts (10 days) | Telephonic induction | Introduction to LEAP programme and the company
Assigning task list
Day 29 - 31 | 21st Jan - 23rd Jan, 2016 | Sponsorships, permissions | Get permission for Campus stall set-up | Printing banners, posters and standees
Follow-up with Campus Buddies Champs
Day 31 - 33 | 24th Jan - 26th Jan, 2016 | Creating awareness | Social media awareness on college portals | Handing over posters to Campus Buddies Champs
|  |  | Word of Mouth | Social media updates
|  |  | Whatsapp activation | PR
|  |  | Putting up posters in colleges | Follow-up with Campus Buddies Champs
Submit screen shots and photos for all awareness creation tools
Day 34 | 27th Jan, 2016 | Buffer day/Preparation day | Announcements & extensive promotion to create noise
Sales champs alignment and promoters
Day 35-46 | 28th Jan - 7th Feb, 2016 | Execution of Campus Buddies | Stall Management, Product placement, promotion, CRM and everything to make it popular | support system for anything & every thing